## Work Updates
ID | Date | Achieved | Next Steps | Comments
0 | 2023-08-08 | Found the original dataset used in the competition provided in the competition Implemented basic functionality to extract the training data into a pandas dataframe Initialized git repository to keep track of changes, I'll leave it private for now Mostly finished the literature review assignment, still missing 2 questions | Publish the local repository to GitHub (don't forget to request the professors' github users) Do basic analysis on each variable Complete the literature review assignment, there's no need to create slides | The original dataset was not located in the address provided in Canvas, I had to do some research to find the proper section in the provided website to get up to the data repository; I added the final link to the jupyter notebook I'll use for this activity
1 | 2023-09-08 | I had the dataset wrong, now I found the updated version, I was using a dataset from 2008 I've finished answering all the literature review questions, I'll keep on editing it until Saturday to see if there are some spelling mistakes | Fully read and add notes on the corrected paper Update the code for activity 2 to include the provided logic to read the data. I think I may need to use Google Colab or the computers at the Data Science Hub lab on campus | Having a wrong dataset was a major drawback, I'll see what I can do tomorrow to recover from the lost days. I'll keep on checking the new papers I found yesterday to see what I can use for the research

## Research
ID | Date | Title | Author | Website | Keywords | Summary | Comments
0 | 2023-08-08 | A systematic literature review of machine learning methods applied to predictive maintenance | Thyago P. Carvalho, Fabrízzio A. A. M. N. Soares, Roberto Vita, Roberto da P. Francisco, João P. Basto, Symone G. S. Alcalá, | A systematic literature review of machine learning methods applied to predictive maintenance - ScienceDirect | Survey, Predictive Maintenance, Machine Learning | Literature review on the most widely used ML techniques for predictive maintenance | It's literally a literature review, it focuses a lot on how they performed the survey, it serves to explain a lot of basic concepts and techniques
1 | 2023-08-08 | Data-Driven Methods for Predictive Maintenance of Industrial Equipment: A Survey | Weiting Zhang, Dong Yang, Hongchao Wang | https://ieeexplore.ieee.org/document/8707108 | Machine Learning, Predictive Maintenance | Better literature review, includes proposed methodologies used | This paper is a great place to start, it includes lots of basic information, but also showcases the basic steps needed to implement a predictive maintenance initiative (Can't access it without SciHub)
|  | A Systematic Literature Review on Transfer Learning for Predictive Maintenance in Industry 4.0 | Testing save |  |  |  | Found it in Biblioteca Tec, I still need to read it, but it looks quite promising